## Documents
| SRA-SAW Integration with PSX | [6 empty] | Documentation Overview |  |  |  | Owner in bold = accountable for document
# | Group | Precise name of document | Kind of document | INM | REQ | Target Date | Relevant/Final Version | Link to document | Status | Scope/Summary/Comment | PM | Owner ES | Owner SWS SMW | Owner SWS | Owner SW
1 | Standard Product Documentation | Administration Guide; Installation and Configuration Guide; etc. | Standard product documentation | n.a. | n.a. | 2016-07-27 |  | https://softwaresupport.hpe.com/; https://irock.jiveon.com/docs/DOC-123381 | 2.20 coming up |  | n.a. | - | - | - | Product Mgmnt
2 | Design |  | Design Incident | y | n.a. | Done |  | Share Point Cloud SvD SAW SRA Integration | Approved | is part of the Dessgn for Incident and Request | Dirk | - | - | Sinan | -
3 | Design |  | Use Cases Incident | y | n.a. | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye | Shivani | - | - | -
4 | Design |  | Field Mapping Incident | y | n.a. | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye/Dirk | Shivani | - | - | -
5 | Design |  | Data Translation Incident | y | n.a. | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye/Dirk | Nancy | - | - | -
6 | Design |  | PSX Mapping Incident | y | n.a. | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye/Dirk | - | - | Geetha | -
7 | Design |  | Design Request/Work Order | n.a. | y | Done |  | Share Point Cloud SvD SAW SRA Integration | in Approval | is part of the Design for Incident and Request | Dirk | - | - | Sinan | -
8 | Design |  | Use Cases Request/Work Order | n.a. | y | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye | Shivani | - | - | -
9 | Design |  | Field Mapping Request/Work Order | n.a. | y | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye/Dirk | Shivani | - | - | -
10 | Design |  | Data Translation Request/Work Order | n.a. | y | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye/Dirk | Nancy | - | - | -
11 | Design |  | PSX Mapping Request/Work Order | n.a. | y | Done | see Design Document | see Design Document | Approved | part of Design Document | Faye/Dirk | - | - | Geetha | -
12 | Design |  | Requirements Tracibility Matrix (RTM) Request/Work Order | n.a. | y | Done | see. Design Document | see Design Document | Approved | part of Design Documen (under Version control) and in ES ALM instance only for Request/Work Order | Faye | Shivani | - |  | -
13 | Build |  | As-Built | y | tbd | 2016-08-19 |  | SWS Share Point for SAW <-> SRA Integration | WIP |  | Dirk | - | - | Geetha; Mary Nancy | -
14 | Test |  | Test Cases Incident | y | n.a. | Done |  | SWS Share Point for SAW <-> SRA Integration | Done | derived from Use Cases | Dirk/Faye | Dominik | - | Harleen | -
15 | Test |  | Test Cases Request/Work Order | n.a. | y | tbd |  | SWS Share Point for SAW <-> SRA Integration | to be started | derived from Use Cases | Dirk/Faye | Dominik | - | Harleen | -
16 | Onboarding (ES/SMS) |  | Onboarding guide | y | tbd | 2016-08-19 |  | SWS Share Point for SAW <-> SRA Integration | WIP | see Admin Guide | Dirk | - | - | Geetha; Richard | -
17 | Onboarding (ES/SMS) |  | End-to-end onboarding flow diagram | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FOnboarding | to be started | End-to-end onboarding flow diagram (with swim lanes) – what parts SWS SMS does / what parts GE&TC does - joint | Glenda/Faye | Nancy; Shivani | Herbert | Sinan | -
18 | Onboarding (ES/SMS) |  | Onboarding RACI – all parties | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FOnboarding | to be started | Onboarding RACI – all parties involved with R,A,C,I – SWS SMS, GE&TC, GSD - joint | Glenda/Faye | Nancy; Shivani | Herbert | Sinan | -
19 | Operations (ES) |  | SIF OLA | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FOnboarding | to be started | we need to templatize one for SAW<>SIF future onboardings – GE&TC only (few questions for PSO) | Glenda/Faye | Nancy | - | - | -
20 | Operations (ES/SMS) |  | End-to-end ongoing support flow diagram | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FOnboarding | to be started | End-to-end ongoing support flow diagram (with swim lanes) – what parts HPE SWS SMS does / what parts ESM Ops does - joint | Glenda/Faye | Nancy; Shivani | Herbert | - | -
21 | Operations (ES/SMS) |  | Ongoing Support RACI – all parties | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FOnboarding | to be started | Ongoing Support RACI – all parties involved (we should stuff this inside the OLA template) - joint | Glenda/Faye | Nancy; Shivani | Herbert | - | -
22 | Operations (ES/SMS) |  | Admin guide | y | tbd | 2016-08-19 |  | SWS Share Point for SAW <-> SRA Integration | WIP | includes onboarding section | Dirk | - | Herbert | Geetha; Richard | -
23 | Sales/Solutioning |  | Cost Model | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FSales%20%26%20Solutioning%20Materials | WIP | (SWS costs for setup of SAW/PSX side + GE&TC costs for onboarding SIF/SM side; depending on whether PSX is deployed as a multi-tennant partner to SIF or as an independent client exchange) SWS IPP (this is not a project deliverable) | Glenda | JP | Herbert | Erwin | Steve
24 | Sales/Solutioning |  | Solution Guidance | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FSales%20%26%20Solutioning%20Materials | to be started | To avoid under or over sell. To know what to sell and how to sell. What is available, what is not (same comments as cost model) | Glenda | JP | - | Erwin | -
25 | Onboarding (ES) |  | SAW blueprint | y | tbd | 2016-08-19 |  | https://hpenterprise.sharepoint.com/teams/0126/Shared%20Documents/Forms/AllItems.aspx?id=%2Fteams%2F0126%2FShared%20Documents%2FOnboarding | to be started | incl. SAW onboarding according to the MWS ask e.g. Steven Anderson for link to standard product documentation | Binesh | Dominik/Jesus | - | - | -

## HPE Theme Colors
Refer to the PowerPoint How-to-Guide for detailed guidance on color usage
Lighter/Darks
| White | Black | HPE grey | HPE slate
R | 255 | 0 | 198 | 66
G | 255 | 0 | 201 | 85
B | 255 | 0 | 202 | 99
Accents and default chart color order
| HPE slate | HPE turquoise | HPE orange | HPE purple | HPE dark steel | HPE grey
R | 66 | 42 | 255 | 97 | 97 | 198
G | 85 | 210 | 141 | 71 | 125 | 201
B | 99 | 201 | 109 | 103 | 120 | 202
Hyperlinks
| HPE dark steel | Dark grey |  | HPE Green
R | 97 | 135 |  | 0
G | 125 | 135 |  | 179
B | 120 | 135 |  | 136
Custom colors
| HPE green | HPE bronze | Dark grey
R | 0 | 135 | 135
G | 179 | 123 | 135
B | 136 | 117 | 135

## Confidentiality
Updating confidentiality footer - Protecting company information
By default this template does not have a confidentiality footer turned on. The footer can be used for confidentiality classification as needed.
Private ¦ Confidential ¦ Internal Use Only
When updating the footer text, you will need to do the following:
– Copy the relevant term from above
– Select all tabs (hold "STRG" and click on each tab that needs to have the footer
–Select "Page Layout" in the ribbonn
– Click on the corner-arrow icon on the left bottom of the "Page Layout" section
– In this pop-up window "Page Selection" select the tab "Header/Footer"
–Click on the "Custom Footer ..." button"
–Paste the relevant confidentiality status in the right section window of this pop-up window
Updating confidentiality footer | All company information, whether sensitive or not, is company property and may only be used for the company’s business purposes. You have a duty to safeguard all company information from misuse or inappropriate disclosure to third parties. Under company policy, there are three standard labels for sensitive information which indicate the level of care to be exercised in handling such sensitive information:
Private: “Private” information is information that has been prepared for Hewlett Packard Enterprise employees at the VP level or above. Examples of “Private” information include information that affects the company’s stock prices. “Private” information must be handled so that access to the information is granted only to a list of individuals maintained by a VP, e.g., through secure communications and authentication in the case of electronically posted information.
Confidential: “Confidential” information may be shared with limited audiences within and outside the company based on a business need to know. Additionally, before “Confidential” information can be shared outside the company, the appropriate contractual protections must be put in place. “Confidential” information includes most information relating to company projects, such as technical data, pricing information, financial information, and business plans.
Internal Use Only: “Internal Use Only” is the label for any information intended for widespread distribution within the company, e.g., to everyone within the company’s firewall or on any of the company’s internal sites. A good example of information receiving this label would be phone information for employees and most organization charts.